## Cover
NeoFin — Information Security Risk Register
ISO/IEC 27001:2022 Aligned ¦ Version 1.0 ¦ March 2026 ¦ Classification: Confidential
Organisation | NeoFin (Digital Neobank — 40M customers, 7,500 staff)
Document Owner | Chief Information Security Officer (CISO)
Prepared by | Yerim Mohamed 21052002 ¦ Faris Sara 22033195 ¦ Ibrahim Sheikh 25006888
Standard | ISO/IEC 27001:2022 / ISO 31000
Risk Methodology | Likelihood × Impact (5×5 matrix) ¦ Hybrid FAIR + Qualitative
Review Cycle | Quarterly (or after any P1/P2 incident)
Classification | Confidential — Internal Use Only
Version | 1.0
Date | March 2026
RISK SCORING MATRIX (Likelihood × Impact = Risk Score)
Critical (20–25) | Immediate executive action required. Existential threat to NeoFin.
High (15–19) | Urgent remediation. Risk owner escalates to CISO within 24 hours.
Very High (10–14) | Significant risk. Remediation plan required within 30 days.
Medium (5–9) | Moderate risk. Managed within standard operations. Reviewed quarterly.
Low (1–4) | Acceptable risk. Monitor and review annually.
RISK TREATMENT OPTIONS
Mitigate | Apply security controls to reduce likelihood or impact.
Transfer | Shift risk via insurance, outsourcing, or contractual obligation.
Accept | Risk within appetite — no further action, monitor only.
Avoid | Eliminate the activity causing the risk entirely.

## Risk Register
NeoFin — Information Security Risk Register
Three Business Domains: IT & Infrastructure ¦ Equipment ¦ Logistics & Support
[7 empty] | PRE-MITIGATION |  |  |  | POST-MITIGATION (RESIDUAL)
Risk ID | Domain | Threat | Vulnerability | Asset(s) Affected | Risk Category | Likelihood (1-5) | Impact (1-5) | Score | Risk Level | Current Controls / Mitigations | Treatment | Residual Likelihood | Residual Impact | Residual Score | Residual Risk Level | Risk Owner | Status
R-001 | IT & Infrastructure | Ransomware Attack | Unpatched systems; phishing entry point; insufficient network segmentation | Core Banking DB (A-005); AWS Infrastructure (A-002); Payment Rails (A-004) | Cyber Threat | 5 | 5 | 25 | Critical | EDR on all endpoints; network segmentation; daily encrypted backups (RTO < 4 hrs); SIEM monitoring; IR retainer engaged; monthly patching cycle. | Mitigate | 2 | 4 | 8 | Medium | CISO | Open — In Remediation
R-002 | IT & Infrastructure | Mass Account Takeover (>50% users) | Weak authentication; credential stuffing; session token vulnerabilities | Customer PII — 40M records (A-006); Authentication System (A-011); Mobile App (A-001) | Cyber Threat | 4 | 5 | 20 | Critical | Biometric MFA mandatory for all customers; rate limiting on login endpoints; anomaly detection via SIEM; JWT short-lived tokens with rotation; bot detection (CAPTCHA). | Mitigate | 1 | 5 | 5 | Medium | CISO | Open — Controls Active
R-003 | IT & Infrastructure | KYC Data Breach (Passports & Selfies) | Inadequate encryption of biometric data; excessive retention; third-party KYC provider compromise | KYC Data — Highly Restricted (A-007); KYC Provider Integration (A-019) | Data Breach / GDPR | 4 | 5 | 20 | Critical | Envelope encryption (AES-256) for all KYC data; hard-delete policy post-verification; DPA with KYC provider; access restricted to authorised staff only. | Mitigate | 2 | 5 | 10 | Very High | DPO | Open — Automated deletion in progress
R-004 | IT & Infrastructure | Sustained DDoS Attack | Internet-facing APIs without sufficient rate limiting or DDoS protection | API Gateway (A-004); Mobile App (A-001); Currency Exchange Engine (A-012) | Availability Threat | 4 | 4 | 16 | High | AWS Shield Advanced (DDoS protection); WAF with rate limiting; auto-scaling; CDN; multi-region active-active deployment; runbook for DDoS response. | Mitigate | 2 | 3 | 6 | Medium | Head of DevOps | Open — Controls Active
R-005 | IT & Infrastructure | Cryptocurrency Platform Exploit | Smart contract vulnerabilities; private key mismanagement; flash loan attacks | Crypto Trading Platform (A-008); Core Banking DB (A-005); HSMs (A-015) | Cyber Threat / Financial | 3 | 5 | 15 | High | HSMs for key storage; multi-sig wallet architecture; penetration testing of crypto module annually; transaction anomaly detection; withdrawal limits enforced. | Mitigate | 2 | 4 | 8 | Medium | CTO | Open — In Remediation
R-006 | IT & Infrastructure | API Gateway Compromise / Injection Attack | SQL injection; SSRF; insecure API design; missing input validation | API Gateway (A-004); Core Banking DB (A-005); Payment Rails (A-004) | Cyber Threat | 3 | 5 | 15 | High | WAF deployed; OWASP Top 10 mitigations enforced; DAST scanning in CI/CD; mandatory PR review for all API changes; parameterised queries enforced. | Mitigate | 1 | 4 | 4 | Low | CTO | Open — Controls Active
R-007 | IT & Infrastructure | Insider Threat — Data Exfiltration | Excessive privileges; lack of monitoring on privileged user activity; disgruntled employee | Customer PII (A-006); Core Banking DB (A-005); KYC Data (A-007) | Insider Threat | 3 | 5 | 15 | High | PAM solution (just-in-time access); all privileged sessions logged; DLP monitoring; UEBA (User and Entity Behaviour Analytics); 4-eyes principle on sensitive operations. | Mitigate | 2 | 4 | 8 | Medium | CISO | Open — Controls Active
R-008 | IT & Infrastructure | Cloud Provider Outage (AWS/GCP) | Over-reliance on single availability zone; insufficient failover testing | AWS Infrastructure (A-002); GCP (A-003); All cloud-hosted services | Availability Threat | 2 | 5 | 10 | Very High | Multi-region active-active deployment; auto-failover; RTO < 4 hrs tested bi-annually; BCP/DR plan (POL-008); SLA with AWS/GCP (99.99% uptime). | Transfer + Mitigate | 1 | 4 | 4 | Low | Head of DevOps | Open — Controls Active
R-009 | IT & Infrastructure | Payment Rail Compromise | Man-in-the-middle on payment APIs; inadequate idempotency controls; replay attacks | Payment Rails (A-004); Core Banking DB (A-005) | Financial / Cyber Threat | 3 | 5 | 15 | High | TLS 1.2+ on all payment communications; idempotency keys on all Duffel/payment API calls; transaction signing; anomaly detection on payment flows; FCA reporting procedures. | Mitigate | 2 | 4 | 8 | Medium | CTO / CISO | Open — In Remediation
R-010 | IT & Infrastructure | SIEM Blind Spot / Logging Failure | Misconfigured log sources; PII in logs; log tampering | SIEM (A-010); All systems generating logs | Operational | 2 | 4 | 8 | Medium | Centralised SIEM with multiple log sources; PII sanitisation enforced in all logging; log integrity monitoring; 24/7 SecOps coverage; quarterly log coverage review. | Mitigate | 1 | 3 | 3 | Low | SecOps Manager | Open — Controls Active
R-011 | Equipment | Employee Laptop Theft / Loss | Unencrypted devices; no remote wipe capability; sensitive data stored locally | Employee Laptops — 7,500+ (A-013); Corporate Mobile Devices (A-016) | Physical / Data Breach | 3 | 3 | 9 | Medium | Full disk encryption (BitLocker/FileVault) on all devices; MDM remote wipe capability; no sensitive data stored locally (cloud-only); device registration and tracking. | Mitigate | 1 | 2 | 2 | Low | Head of IT | Open — Controls Active
R-012 | Equipment | Phishing Attack Leading to Credential Theft | Staff susceptibility to phishing; SMS 2FA bypass; credential reuse | Employee Laptops (A-013); Authentication System (A-011); All corporate systems | Cyber Threat / People | 4 | 4 | 16 | High | Hardware MFA tokens for privileged staff; quarterly phishing simulations; mandatory annual security awareness training; email filtering with anti-phishing; DMARC/SPF/DKIM enforced. | Mitigate | 2 | 3 | 6 | Medium | CISO / HR | Open — Controls Active
R-013 | Equipment | HSM (Hardware Security Module) Compromise | Physical access to HSM; firmware vulnerabilities; insider threat at HSM level | HSMs (A-015); Encryption keys for all Tier 1 data | Cyber Threat / Physical | 2 | 5 | 10 | Very High | HSMs in locked, access-controlled cabinets; tamper-evident seals; maintenance by certified engineers only; key ceremony procedures; dual control for key operations. | Mitigate | 1 | 5 | 5 | Medium | CISO | Open — Controls Active
R-014 | Equipment | Unpatched Endpoint Vulnerability | Delayed patching; end-of-life software; shadow IT devices | Employee Laptops (A-013); Corporate Devices (A-016) | Cyber Threat | 3 | 4 | 12 | Very High | Monthly patching cycle via MDM; critical patches within 72 hours; EDR detects unpatched CVEs; no unapproved software allowed; MDM compliance reporting. | Mitigate | 1 | 3 | 3 | Low | Head of IT | Open — Controls Active
R-015 | Equipment | Rogue / Unauthorised Device on Corporate Network | Inadequate network access control; BYOD risks; MAC spoofing | Network Hardware (A-014); VPN Infrastructure (A-017); All internal systems | Cyber Threat | 2 | 4 | 8 | Medium | 802.1X network access control; VPN required for remote access; MDM enrollment mandatory; network segmentation limits blast radius; IDS alerts on unknown devices. | Mitigate | 1 | 3 | 3 | Low | Head of IT | Open — Controls Active
R-016 | Logistics & Support | Card Printing Vendor Breach | Third-party vendor with access to cardholder data; weak vendor security controls | Card Printing Vendor Data (A-018); Customer PII (A-006) | Supply Chain / Data Breach | 3 | 4 | 12 | Very High | Supplier Security Policy (POL-009); annual vendor security assessments; DPA signed with card printer; cardholder data minimisation — only necessary data shared; PCI DSS compliance required of vendor. | Transfer + Mitigate | 1 | 3 | 3 | Low | COO | Open — DPA Pending
R-017 | Logistics & Support | KYC Provider Compromise (Third-Party) | Third-party KYC platform breach; inadequate DPA; excessive data sharing | KYC Provider Integration (A-019); KYC Data (A-007) | Supply Chain / GDPR | 3 | 5 | 15 | High | DPA with KYC provider (in progress); data minimisation — only required fields shared; KYC data hard-deleted after verification; annual security assessment of provider; contractual breach notification within 24 hrs. | Transfer + Mitigate | 2 | 4 | 8 | Medium | DPO | Open — DPA In Progress
R-018 | Logistics & Support | Social Engineering of Customer Support Staff | Inadequate identity verification by support agents; vishing/pretexting attacks | Customer Support Systems (A-020); Customer PII (A-006) | People / Cyber Threat | 3 | 4 | 12 | Very High | Strict identity verification protocol for support agents (cannot act without 2-factor customer verification); regular social engineering awareness training; call recording and audit; escalation procedure for suspicious requests. | Mitigate | 2 | 3 | 6 | Medium | COO | Open — Training Active
R-019 | Logistics & Support | Third-Party DPA Non-Compliance / GDPR Breach | DPAs not signed with all sub-processors; inadequate contractual protections | All third-party data processing relationships (A-021) | Regulatory / GDPR | 4 | 4 | 16 | High | DPA signing process initiated with all 6 processors (Descope, SendGrid, Supabase, Stripe, All Aboard, Duffel); legal team tracking; no live data processing until DPAs signed. | Mitigate | 2 | 3 | 6 | Medium | DPO | Open — In Progress (Critical)
R-020 | Logistics & Support | Supply Chain Software Compromise (SolarWinds-type) | Malicious code injected via third-party software update; inadequate SBOM tracking | All systems dependent on third-party software | Supply Chain / Cyber Threat | 2 | 5 | 10 | Very High | Software Bill of Materials (SBOM) tracked; all third-party libraries scanned for CVEs; code signing enforced; dependency updates reviewed before deployment; supplier security assessments annually. | Mitigate | 2 | 4 | 8 | Medium | CTO / CISO | Open — Controls Active

## Risk Heat Map
NeoFin — Pre-Mitigation Risk Heat Map (5×5 Matrix)
IMPACT → (1=Insignificant → 5=Catastrophic) |  | 1 — Rare | 2 — Unlikely | 3 — Possible | 4 — Likely | 5 — Almost Certain
| 5 — Catastrophic | 5 | 10 R-008 | 15 R-017 R-020 | 20 R-005 R-006 R-007 R-009 R-013 | 25 R-001 R-002 R-003
| 4 — Major | 4 | 8 R-010 R-015 | 12 R-014 R-016 R-018 | 16 R-012 R-019 | 20
| 3 — Moderate | 3 | 6 | 9 R-011 | 12 R-004 | 15
| 2 — Minor | 2 | 4 | 6 | 8 | 10
| 1 — Negligible | 1 | 2 | 3 | 4 | 5
LIKELIHOOD → (1=Rare → 5=Almost Certain)

## Treatment Plan
NeoFin — Risk Treatment Plan (Priority Order)
Risk ID | Risk Name | Domain | Treatment | Priority | Remediation Actions | Owner | Target Date
R-003 | KYC Data Breach | IT & Infra | Mitigate | P1 — CRITICAL | Implement automated hard-delete jobs for KYC data post-verification. Complete DPA with KYC provider. Restrict access to named individuals only. | DPO | April 2026
R-019 | DPA Non-Compliance | Logistics | Mitigate | P1 — CRITICAL | Sign DPAs with all 6 sub-processors (Descope, SendGrid, Supabase, Stripe, All Aboard, Duffel) before any live data processing begins. | DPO | April 2026
R-002 | Mass Account Takeover | IT & Infra | Mitigate | P1 — CRITICAL | Enforce biometric MFA for all 40M customers. Implement UEBA to detect account takeover patterns. Rate limit all auth endpoints. | CISO | April 2026
R-001 | Ransomware Attack | IT & Infra | Mitigate | P1 — CRITICAL | Complete network micro-segmentation. Test DR recovery within 72 hours. Red team ransomware simulation exercise. | CISO | May 2026
R-009 | Payment Rail Compromise | IT & Infra | Mitigate | P1 — CRITICAL | Implement idempotency keys on all Duffel and payment API calls. Add transaction signing. Enable FCA incident reporting workflow. | CTO / CISO | April 2026
R-017 | KYC Provider Compromise | Logistics | Transfer + Mitigate | P2 — HIGH | Complete DPA with KYC provider. Implement data minimisation. Contractual 24hr breach notification obligation. | DPO | April 2026
R-005 | Crypto Platform Exploit | IT & Infra | Mitigate | P2 — HIGH | Commission penetration test of crypto module. Implement multi-sig for withdrawals above threshold. HSM key rotation procedure. | CTO | May 2026
R-007 | Insider Threat | IT & Infra | Mitigate | P2 — HIGH | Deploy UEBA solution. Implement just-in-time PAM. Quarterly access rights review. DLP alerts on bulk data export. | CISO | May 2026
R-016 | Card Printing Vendor Breach | Logistics | Transfer + Mitigate | P2 — HIGH | Complete DPA with card printer. Annual security assessment of vendor. Minimise cardholder data shared. | COO | April 2026
R-012 | Phishing / Credential Theft | Equipment | Mitigate | P3 — MEDIUM | Hardware MFA tokens for all privileged users. Monthly phishing simulations. DMARC enforcement for all domains. | CISO / HR | May 2026
R-004 | DDoS Attack | IT & Infra | Mitigate | P3 — MEDIUM | Enable AWS Shield Advanced on all public endpoints. Quarterly DDoS runbook exercises. Capacity stress test. | Head of DevOps | June 2026
R-018 | Social Engineering — Support | Logistics | Mitigate | P3 — MEDIUM | Mandatory monthly social engineering awareness training for all support staff. Implement 2-factor customer verification protocol. | COO | May 2026
R-020 | Supply Chain SW Compromise | Logistics | Mitigate | P3 — MEDIUM | Complete SBOM for all third-party dependencies. Enforce code signing. Subscribe to CVE alert feed for all libraries. | CTO / CISO | June 2026
R-014 | Unpatched Endpoints | Equipment | Mitigate | P3 — MEDIUM | Enforce MDM compliance — non-compliant devices auto-quarantined. Critical patch SLA: 72 hours from CVE disclosure. | Head of IT | Ongoing
R-011 | Laptop Theft | Equipment | Mitigate | P4 — LOW | Verify 100% MDM enrollment. Confirm full disk encryption on all devices. Test remote wipe quarterly. | Head of IT | Ongoing